## Sprint
Backlog Item | Task | Task Owner | Total Story Points | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8
|  |  |  | 2020-10-05 | 2020-10-12 | 2020-10-26 | 2020-11-09 | 2020-11-23 | 2020-11-30 | 2020-12-04 | 2020-12-11
|  |  |  | 256 | 249 | 199 | 149 | 99 | 49 | 11 | 0 | Ideal Burndown
|  |  | 12 | 256 | 249 | 221 | 198 | 126 | 38 | 0 |  | Remaining Hrs (Total)
Team Formation and Project Management Setup | Decide on Tech stats | All | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Requirement Analysis and Discussion | All | 3 | 3 | 0 | 0 | 0 | 0 | 0
Plan and Strategize overall design | Design Architecture | Prerana | 3 | 3 | 0 | 0 | 0 | 0 | 0
| Design and Create Database schema, tables | Deepthi, Prerana | 12 | 12 | 12 | 12 | 9 | 3 | 0
| Businsess Logic and Design finalization | All | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Design UI Wireframes | Aditya, Prashanth | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Finalize implemenation workload based on features | All | 2 | 2 | 2 | 0 | 0 | 0 | 0
Early development and environment readiness | Develop Frontend Code Base | Aditya | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Develop Backend Code Base | Deepthi, Prerana | 5 | 5 | 5 | 0 | 0 | 0 | 0
HomeFinder Fontend Development | Develop UI for Admin functionalities - Frontend | Prashanth | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Develop UI for User Core functionalities - Frontend | Prashanth | 7 | 7 | 7 | 7 | 3 | 3 | 0
| Develop UI for Listings functionalities - Frontend | Aditya | 33 | 33 | 33 | 33 | 30 | 15 | 0
| Setup Algolia and render frontend | Aditya | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Develop UI for Favorites functionalities - Frontend | Aditya | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Develop UI for Applications functionalities - Frontend | Prashanth | 14 | 14 | 14 | 14 | 14 | 11 | 0
| Deploy Frontend on Heroku, staging, prod environments | Aditya | 3 | 3 | 3 | 3 | 3 | 3 | 0
HomeFinder Backend Development | Design REST APIs for Admin functionalities - Backend | Deepthi | 17 | 17 | 17 | 17 | 12 | 8 | 0
| Design REST APIs for User Core functionalities - Backend | Deepthi | 9 | 9 | 9 | 9 | 4 | 1 | 0
| Design REST APIs for Listings functionalities - Backend | Prerana | 26 | 26 | 26 | 26 | 23 | 6 | 0
| Create Algolia Index and deployment environments, integrate backend | Prerana | 4 | 4 | 4 | 4 | 4 | 0 | 0
| Design REST APIs for Favorites functionalities - Backend | Prerana | 10 | 10 | 10 | 10 | 7 | 0 | 0
| Design REST APIs for Applications functionalities - Backend | Deepthi | 15 | 15 | 15 | 15 | 15 | 4 | 0
| Deploy Backend on Heroku, staging, prod environments | Prerana | 3 | 3 | 3 | 3 | 3 | 0 | 0
Testing | Test HomeFinder Backend APIs on staging and prod environments | Deepthi, Prerana | 22 | 22 | 22 | 22 | 22 | 22 | 0
| Test HomeFinder Application on staging and prod environments | All | 10 | 10 | 10 | 10 | 10 | 10 | 10
Documentation | Maintain artifacts and related documentation | All | 28 | 28 | 28 | 28 | 28 | 28 | 28
Total Story Points : 256 Sprint 1 is shortest and warm sprint, so estimated to deliver 7 points Sprint 2: 50 Sprint 3 : 50 Sprint 4: 50 Sprint 5: 50 Sprint 6: 50